IDP Unit

2025/26

Tokologo IDP Process Plan

Tokologo Local Municipality

Private X 46

BOSHOF

8340

TABLE OF CONTENT

| Introduction | Page 2 |
| --- | --- |
| Review | Page 3 |
| 1.1.The process plan 1.2 Key power and function of Tokologo 1.3 Distribution of roles and responsibility in the IDP Process 1.3.1 Local Municipality | Page 4 |
| 1.3.2 District Municipality 1.3.3 Sector Departments | Page 5 |
| 1.3.4 Municipal Council 1.3.5 Plenary 1.3.6 Ward Councillors 1.3.6.1 Ward Committees 1.3.6.2 C.D.W ‘s | Page 6 |
| 1.3.7 Municipal Manager 1.3.8 Heads of Departments and Officials 2.1 The IDP Steering Committee | Page 7 |
| 2.1.1 Terms of reference for the steering committee 2.1.2 IDP Representative Forum 2.1.3 Terms of reference of the IDP Representative Forum | Page 8 |
| 2.1.4 Code of Conduct – IDP Representative forum 2.1.5 Planning and Public participation processes 3 Annual IDP review/Amendment planning process Phase 1 Analysis Phase 2 Strategies Phase 3 Projects | Page 9 |
| Phase 4 Integrated Phase 5 Approval | Page 10 |
| 4 Tokologo Local Municipality IDP and Budget process time-frame | Page 11-12 |

1THE PLANNING PROCESS

1.1   INTRODUCTION

Preparing an IDP is a legal requirement in terms of the municipal System Act (MSA); however that it’s not the only reason why municipality must prepare the plan. Under the new constitution, municipalities have been awarded major developmental responsibilities to ensure that the quality of life of its citizens is improved. The new role for local government includes provision of basic services, creation of jobs, promoting democracy and accountability and eradication of poverty. Preparing and implementing the IDP enables the municipality to manage the process of fulfilling its developmental responsibilities.

Through the IDP, the municipality is informed about the problems affecting its municipal area and, being guided by information on available resources, is able to develop and implement appropriate strategies and projects to address the problem.

The Service Delivery and Budget Implementation Plan (SDBIP) details the implementation of service delivery and the Budget for the financial year in compliance with the MFMA (Act 56 of 2003), The SDBIP serves as a contract between the administration, Council and community, exposing the objectives set by council as quantifiable outcomes that can be implemented by the administration over the next Twelve Months.

The SDBIP facilitates the process of holding management accountable for their performance, It provide the basis for measuring performance in the delivery of services, this therefore means that the IDP and Budget cannot be implemented without the SDBIP.

The Annual Budget and the IDP are inextricably linked to one another, something that has been formalized through the promulgation of the Local Government: Municipal Finance Management Act NO: 56 OF 2003, Chapter 4 of Section 21(1) of the Municipal Finance Management Act indicate that.

The Mayor of the municipality must:

- At least 10 months before the start of the Budget year, table in the Municipal Council a time Schedule outlining key deadlines for –

The preparation, tabling and approval of the Annual Budget;

The Annual review of –

aa) The Integrated development plan in terms of Section 34 of the Municipal System Act, and

bb) The Budget related policies

- The Tabling and adoption of any amendments to the Integrated development plan and the Budget related policies, and

- The consultative processes forming part of the processes referred to in subparagraph (i)

Review

‘Review” means a process whereby the IDP is evaluated in terms of the municipality’s performance as well as changed circumstances (IDP Guide VI P119). The IDP review is the reflection of the impact of successes as well as corrective measures to address the problem.

The IDP is also reviewed in the light of changing internal and external circumstances impacting on the priority issues, objectives, strategies, projects and programme of the IDP.

In terms of section 34 of the municipal Systems Act, (Act No 32 of 2000), Municipal Council.

- Must review its integrated development plan.

- Annually in accordance with an assessment of its performance measurements in terms of section 41, and

- To the extent that changing circumstances so demand, and

- May amend its integrated Development Plan in accordance with a prescribed process.

The IDP has to be review annually in order to:

- Ensure its relevance to the municipality’s strategic plan

- Inform other components of the municipal business processes including institutional transformation, financial planning and budget cycle

- Inform the cyclical inter-departmental planning and budget cycle

- Address the shortcoming in the original IDP preparations and incorporate improvements.

- Consider power and functions.

The outcome of the review process may include:

- A refined understanding of the situation around priority issues.

- Amended and additional objectives as a result of new information

- Review and new projects

The review activities include addressing of:

- New data

- Comments from the MEC

- Comments from the Public

- Revised projects and programmes

- Better aligned Tokologo IDP with the District to both the national spatial development perspective and the Free State Provincial Growth and Development Strategy.

    - The Process Plan

The purpose of the process plan is to outline and describe how the Tokologo Municipality will implement the new system of planning in its area of jurisdiction. The Process Plan is similar to a business plan as it sets out clear parameters and the legal framework within all stakeholders are going to operate during the formulation of the IDP. The process plan also spell out the specific timeframes, targets and deliverables during the formulation of the IDP documents.

The municipality planning regulations and performance management regulations, 2001 section 3, stipulates that only a member or committee of a municipal council may introduce proposal for amending the municipality ‘s integrated development plan in the council.

1.2   Key Power and functions of Tokologo Local Municipality

| No | Local Municipality | District Municipality | Provincial Department |
| --- | --- | --- | --- |
| 1 | Municipal Public works | Bulk infrastructure | Provision of Housing |
| 2 | Internal Road infrastructure | Integrated Planning | Library services |
| 3 | Bulk Water supply and reticulation | Fire fighter |  |
| 4 | Sanitation | Fresh produce markets and abattoirs |  |
| 5 | Solid Waste Disposal | Cemeteries and Crematoria |  |
| 6 | Bulk Electricity Supply | Local Tourism |  |
| 7 | Fire Fighter Service | Fire Fighting Service (Tswelopele and Masilonyana) |  |
| 8 |  | Municipal Airports |  |
| 9 |  | Waste Management service |  |
| 10 |  | Municipal Health services |  |
| 11 |  | Integrated Transport Service |  |
| 12 |  | Municipal Airport (except for Matjhabeng and Nala) municipalities. |  |

1.3 DISTRIBUTION OF ROLES AND RESPONSIBILITY IN THE IDP PROCESS

1.3.1 Local Municipality

The role of the municipal government is to:

- Prepare, decide on and adopt a process Plan

- Undertake the overall management and co-ordination of the planning process which includes ensuring that.

- All relevant actors are appropriately involved,

- Appropriate mechanisms and procedures for public consultation and participation are applied,

- Planning events are undertaken in accordance with the time schedule,

- Planning process is related to the real burning issues in the municipality, that it is a strategic and implementation-oriented process, and

- The sector planning requirements are satisfied.

- Adopt and approve the IDP.

- Adjust the IDP in accordance with the MEC of Cooperate governance and Traditional Affair’s proposal.

- Ensure that the annual business plans, budget and land use management decision are linked to and based on the IDP.

1.3.2 District Municipality

The District Municipality has the same roles and responsibility as local municipality, but only related to the preparation of a District IDP.

The role of the District Municipality on a local level is the co-ordination of the IDP Processes of the local municipalities:

- Ensuring horizontal alignment of the IDPs of the municipalities in the district council area,

- Ensuring vertical alignment between district and local planning,

- Facilitation of vertical alignment of IDPs with other sphere of government and sector department, and

- Preparation of joint strategy workshop with local municipality, provincial and national role-players and other subject matter specialists.

1.3.3 Sector Departments

Ensuring vertical/sector alignment between provincial sector departments/provincial strategic plans and the IDP process at local/district level by:

- Guiding the provincial sector departments’ participation in and their required contribution to the municipal planning process, and

- Guiding them in assessing draft IDP and aligning their sector programmes and budgets with the IDPs.

- Efficient financial management of provincial IDP grants.

- Monitoring the progress of the IDP processes.

1.3.4 Municipal Council

As the ultimate political decision-making body of the municipal Council has to:

- Consider and adopt a process Plan

- Consider, Adopt and approve the IDP

1.3.5 Plenary

As the senior governing body of the municipality, they have to:

- Decide on the Process plan.

- Be responsible for the overall management, co-ordination and monitoring of the process and drafting of the IDP, or delegate this function to the Municipal manager.

- Approve nominated persons to be in charge of the different roles, activities and responsibilities of the process and drafting.

1.3.6 Ward Councillors

Councillors are the major link between the municipal government and the residents. As such, their role is to:

- Play a leading role in the IDP process.

- Represents their constituency’s needs and aspiration.

- Mobilize community to participate in the IDP process.

1.3.6.1 Ward Committees role is to.

- Identify the critical issues facing its area.

- Provide a mechanism for discussion, negotiation and decision-making between the    stakeholders, including municipality.

- Form a structure links between the IDP Representative Forum and the Community of each area, and

- Monitor the performance of the planning and implementation process concerning its area.

1.3.6.2 CDW’s role is to.

- Assist communities with their needs and with the necessary information on what government is doing.

- Provide information regarding the government work taking place in communities, they remain accountable to councilors.

- Link the communities with government services and relay community concerns and problems back to government structures

- Improve government- community network.

1.3.7 Municipal Manager

The Municipal Manager or a senior official being charged with the function of the IDP Manager on his/her behalf has to manage and co-ordinate the process. This includes to:

- Prepared the Process Plan

- Undertake the overall management  and co-ordination of the planning process,

- Ensure that all relevant actors are appropriately involved

- Nominate persons in charge of different roles

- Be responsible for the day-to- day management of the drafting process,

- Ensure that the planning process is participatory, strategic and implementation orientated and is aligned with the satisfies sector-planning requirements,

- Respond to comments on the draft IDP from the public, horizontal alignment and other spheres of government to the satisfaction of the municipal council,

- Ensure proper documentation of the results of the planning of the IDP document, and

- Adjust the IDP in accordance with the MEC for Co-operative government and Traditional Affairs.

Even if the municipal manager delegates some of these functions to an IDP Manager on his/her behalf, he/she is still responsible and accountable.

1.3.8 Heads of Departments and Officials

As the person in charge for implementing IDPs, the technical/sectional officers have to be fully involved in the planning process to:

- Provide relevant technical, sector and financial information for analysis for determining priority issues.

- Contribute technical expertise in the consideration and finalization of strategies and identification of projects,

- Provide departmental operational and capital budgetary information,

- Be responsible for the preparation of project proposal , the integration of projects and sector programmes, and

- Be responsible for preparing amendments to the draft IDP for submission to the municipal council for approval and the MEC for Cooperate government and Traditional Affairs.

  - The IDP Steering Committee

The Steering Committee is a technical working team of dedicated heads of Departments and senior officials who must support the IDP Manager to ensure the smooth planning process. The IDP Manager is responsible for the process but will delegate some functions to the members of the steering committee and will be constituted as follows:

| Names | Designation |
| --- | --- |
| Mr M Sehloho | Acting Municipal Manager |
| Mr T Matile | Chief Financial Officer |
| Mr C Tlhokwe | Cooperate Service Director |
| Mr M Hlazo | Acting Technical Director |
| Mr M.W Merahe | Acting IDP Manager |
| Lejweleputswa District Municipality | IDP Support |
| Provincial CoGTA | IDP Support |

- Chairperson  : Acting Municipal manager

- Secretariat    : Official of the municipality (IDP Unit)

- Member         : Heads of Departments and other identified managers

    - Terms of reference for the Steering Committee

- The Steering Committee will be responsible for the establishment of the IDP Representative Forum.

- Provide terms of reference for the IDP representative Forum, subcommittee and the various planning committee

- Commission research studies

- Consider and comment on inputs from sub-committee, study teams and consultants, inputs from Provincial sector departments and service providers

- Process, summarize and draft outputs and make recommendations to Executive Committee which is headed by the Mayor/Speaker as the ultimate custodian of the IDP on behalf of council.

- Prepare and submit reports to the IDP Representative Forum.

    - IDP Representative Forum

The IDP Representative Forum is the structure which institutionalizes and guarantees representative participation in the IDP process. The selection of members to the IDP representative forum has to be based on criteria which ensure geographical, economic and social representation and as follows:

- Chairperson: Political Head of the institution

- Secretary: The IDP Steering Committee secretariat

- Members: Ward Committee chairpersons & CDW’s

- Heads of Departments/Senior Officials

- Stakeholders representatives of organized groups (e.g. NGO’s & CBO’s)

- Resource person/organizations (Doctor/Economist)

- Community Representatives (e.g. Transport Forum, Health Forum & CPF)

    - Terms of reference of the IDP Representative Forum

- To represent the interest of their constituents in the IDP process

- Provide an organizational mechanism for discussion, negotiation and decision-making between the stakeholders and the municipality.

- Ensure there is adequate communication and consensus on priority issues among all the stakeholder representatives, and

- Monitor the performance of the planning and implementation of the IDP and its process.

    - Code of conduct – IDP Representative Forum

The code of conduct will at least include the following:

- Meeting schedule (frequency and attendance)

    - Planning and Public participation processes

3. Annual IDP Review planning process

PHASE 1: ANALYSIS

- Community and Ward Committee meeting

- Institutional meetings (Technical/Political)

- Stakeholders meetings

- Sample survey (if necessary)

- Opinion polls (on certain issues if necessary)

- Desktop analysis

PHASE 2: STRATEGIES

Strategic workshop, with IDP Representatives Forum, provincial and national departments and selected representatives of stakeholder organizations and resource people must be convened as planned.

Stimulation for success of these public events must be through public meetings, press conference, etc.

The outcome of these meetings should give impetus towards addressing pressing challenges that have been identified by stakeholders in order of priorities and municipal delegated functions.

PHASE 3: PROJECTS

- Municipality wide projects/ Programmes identified from:

- Internal departments especially the ones that are short- to medium term and requiring further budgetary requirements,

- Stakeholders inputs (departmental, community priorities)

PHASE 4: INTEGRATED

District integrated Plan: Incorporation of sector plans must be done at this stage. Contribution must have been accessed through set meetings.

PHASE 5: APPROVAL

- Broad public discussion/ consultation process within community/ stakeholders organizations.

- IDP Representative Forum.

- Council resolution taken on approving the document for implementation in the next financial year

| TOKOLOGO MUNICIPALITY IDP AND BUDGET TIME-FRAME |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | ACTION | DELIVERABLE/OUTPUT | RESPONSIBLE | ACTION DATE |
| 1 | IDP to be reviewed/amendment | Reviewed/Amend IDP | MM and Mayor | 01 September 2024 to 31 May 2025 |
| 2 | Prepare process plan 2025/2026 |  | IDP Manager | July 2024 submitted to MM’s office |
| 3 | Proposed IDP process plan 2025/2026 | Present Proposed IDP Process plan to IDP Representative forum | IDP Manager and MM | August 2024 |
| 4 | Submission of process plan for adoption by council | Adopted process plan | Municipal manager | On or before 30 August 2024 |
| 5 | Formation of IDP committee to deal with comments made during IDP Engagement |  | Municipal manager and Directors | September 2024 |
| 6 | IDP Steering committee quarterly performance review-municipal SDBIP | Quarterly Performance Assessment Results | Municipal manager and Directors | October 2024 |
| 7 | Start community consultation process to ensure public participation |  | Mayor and Municipal manager | September to November 2024 |
| 8 | IDP Analysis phase draft review report to steering committee |  | IDP Manager and Municipal manager | October 2024 |
| 9 | Estimates available resources and provide guidance for forward of Budget request inputs to all relevant person |  | CFO | October 2024 |
| 10 | Review Key Objectives, strategies and Projects | Reviewed Key Objective, strategies and Projects | Municipal manager, IDP Manager, IDP Steering com | November 2024 |
| 11 | Preparation of a summary of available funds from Internal funds and External funds (Grants) |  | CFO | November 2024 |
| 12 | Prioritization of reviewed projects list for 2025/2026 from the 2024/2025 IDP. Compile report on the needs for the year/s ahead obtained from the community and other stakeholders | Project list | MM, IDP Manager and Steering Committee | December 2024 |
| 13 | Submission of detailed estimates by MM, Directors and Councillors to CFO | Budget Estimates | MM, Directors and Politicians | December 2024 |
| 14 | Assess Financial feasibility of proposed new projects based on the existing and potential funds | Proposed new project list | All Directors | January 2025 |
| 15 | Meeting with relevant Officials (First draft Budget meeting) | Draft Budget | CFO | January 2025 |
| 16 | Meeting with relevant Officials (Second draft Budget meeting) |  | CFO | January 2025 |
| 17 | Consider of Draft Budget by council |  | CFO | March 2025 |
| 18 | Tabling of MTEF Budget and IDP to Council for approval as First Drafts | Draft Budget and IDP items to Council | Mayor | On or before 31 March 2025 |
| 19 | Publicized tabling Draft Budget and Draft IDP within 5 days on municipal website, media and municipal Offices | Publicized Draft Budget and Draft IDP | MM and CFO | April 2025 |
| 20 | Submit copies of Draft IDP and Draft Budget to Provincial CoGTA and Treasury | Submission of Draft IDP and Draft Budget | MM and CFO | April 2025 |
| 21 | Second leg of IDP and Budget participation process start: comments, additions and proposal by stakeholders | Receiving comments, additions and proposal from stakeholders | MM, Directors and Politicians | April 2025 |
| 22 | Finalize IDP and Budget, prepare and submit report for inclusion in council Agenda, Considering stakeholders inputs |  | MM and CFO | May 2025 |
| 23 | Mayor finalize the Draft IDP and Draft Budget 2025/2026 |  | MM and CFO | May 2025 |
| 24 | Submission of Draft IDP and Budget for 2025/2026 for approval by council | Approval of IDP and Budget by Council | MM and CFO | On or before 30 May 2025 |
| 25 | Advertise the Approve Final Budget and IDP to the website and media | Advertised the approve Budget and IDP within 14 days | MM and CFO | June 2025 |
| 26 | Submit the approved Budget and IDP to Provincial COGTA and Treasury | Submission of Final Budget and IDP | MM and CFO | June 2025 |
| 27 | Submit Draft SDBIP to Mayor within 24 days after the approval of Budget and IDP | Final municipal SDBIP | MM | July 2025 |